## Hoja1
| Task | Estimated time | Total Time |  | Tarea | Estimación | Tiempo final |  | Tarea | Estimación | Tiempo final
Albert | Sistema movimiento fondo | 120 minutes | 60 | Pol J | Recortar imagen fondo | 60 minuts | 20 | Pol G | Crear modulo
| Punch, jump, kick, crushing wave animation | 60 minutes | 120 | Pol J | Background del mapa de Haohamru(con todas sus animaciones) | 60 minuts | 110
| Scene change, module music | 300 minutes | 420 | Pol J | Crear modulos menu y VictoryHaohmaru, y backgrounds | 45 minuts | 70
| Projectile module, collision layout, projectile animation | 300 minutes | 270 |  | Crear modulos player 2(sprites, acciones,etc) | 45 minuts | 45
| New input | 120 minutes | 90 |  | Arreglar patada | 60 minuts | 50
| Punch and jump | 60 minutes | 40
| Face opponent | 90minutes | 120
| Hitbox | 120 minutes | 120
| Fix module input | 60 minutes | 30
| Player 2 | 120 minutes | 80
| Fonts | 180 minutes | 120
| Timer | 60 minutes | 70
| Music fix | 30 minutes | 20
| Camera | 120 minutes | 60
| Impacts between players | 30 minutes | 30
| Camera limits | 60 minutes | 45
| Scene mapping | 20 minutes | 30
| Combo | 30 minutes | 45
| Block, Pauses ;before and after match; Best of 3 rounds, auto win, auto lose | 150 minutes | 120
| Bugfixing | 60 minutes | 180
| Bugfixing | 120 minutes | 240